## Sheet1
| Week 1 (March 13th) | Week 2 (March 20th) | Week 3 (March 27th) | Week 4 (April 3rd) | Week 5 (April 10th) | Week 6 (April 17th)
Assignment Due Dates | Plan (Mar 12th) | Milestone 1 (Mar 19th) |  | Milestone 2 (April 3rd) |  | Final Submission (April 16th)
Adam | Health Script | Multiplayer & Game Structure | Battlecry Mechanic & Game Structure |  | Game Polish
Liam | Implementing Guns with Bullet Physics as Gun Variants |  | Movement Mechanic |  | New Weapons
Felix | Capture The Flag Gamemode |  | Team Deathmatch Gamemode |  | UI Design/Systems
Firaas | Capture The Flag Maps |  | Team Deathmatch Maps |  | Pickups & Powerups
| Design Questions |  |  | Measurables
1 | How much does modifying the accuracy of the player effect how well the player can hit their target consistently? |  |  | The hit vs. miss ratio of 150 shots at various magnitudes of accuracy spikes periodically.
2 | Would adding a new weapon speed or slow down the pace of gameplay? |  |  | The average amount of time 3 rounds take without the weapon takes vs with the weapon.
3 | Would adding many new mechanics make the game too complicated for new players? |  |  | 1 - 5 ratings on how easy it felt to get a grasp on the game submitted by playtesters (with an added description of why they gave the number they did)